HOWARD HANNA COMMERCIAL
Project Status Update

Latest information from Base Engineering Company handling the project.

Project accepted for review as a Major Subdivision Review by Polk Township.

Sanitary and stormwater infiltration testing completed for all proposed lots (Creekside Consultants).

Submission to Monroe County Planning Commission (review letter dated 3/24/2026).

Sewage Planning Module submitted to Polk Township and currently under review (dated 2/23/2026).

Trip Generation Study supporting exemption from a Traffic Impact Study (dated 11/25/2025).

15-sheet Major Subdivision Plan Set completed (requires revision for layout changes and review comments).

PNDI Receipt and USFWS clearances obtained (12/17/2025).

Stormwater Drainage Report and Post Construction Stormwater Management Narrative completed (requires revision for layout changes and review comments).

Wetland and Waters Identification & Delineation Report completed (June 2024).

Most recent Polk Township review letter dated 4/2/2026.

Base Engineering attended multiple Planning Commission meetings regarding SALDO waivers.

Drainage swale waiver deemed acceptable provided stormwater design accommodates drainage.

Driveway spacing waiver: Township determined proposed private roadway and adjacent driveway spacing is acceptable based on sight distance information (review letter dated 6/9/2026).

Safe sight distance concern for proposed Lot 1 has been eliminated after Lot 1 revisions.